## Sheet1
S. No. | Task | Status | Expected Date
1. a. | Solve issue with authentication | done | Week One
1. c. | Allowing forming of groups within channels and initiating a chat | done | Week One
1. d. | Chat with multiple Teams | done | Week One
2. a. | Organisation Wall | in progress | Week Two
2. b. | Notifications | pending | Week Two
2. c. | URL Scraping, file icon | in progress | Week Two
2. d. | Previously registered user directed to login | in progress | Week Two
3. a. | Team Wall | pending | Week Three
3. b. | User Profile (Personal details + Photograph) | pending | Week Three
3. c. | Allow team lead to modify team | pending | Week Three
3. d. | Validation of forms | pending | Week Three
3. e. | TDD testcases in existing code | pending | Week Three
Parking Lot
Comments